## Delay event register
Delay event register
Kept from mobilisation, updated weekly. Yellow cells are yours to fill in; grey cells calculate themselves. One row per event, opened the day the event is first apparent — not the day a claim is contemplated.
Template — the clause references, notice windows and status vocabulary must be replaced with the ones in the executed contract.
Ref | Event — what happened | Date event occurred | Date first apparent | Notice window (days) | Notice due | Notice served | Days to spare | Status | Notice ref | Clause relied on | Time or money | Activities affected | Critical at the time? | Days claimed | Days granted | Particulars due | Particulars served | Records attached | Concurrent contractor delay? | Current status | Notes
Sequential. EV-001, EV-002. | One or two sentences of fact. No characterisation. | The instruction, condition or occurrence. | The date the clock starts on most forms. Evidence it. | Read off the executed contract, not a standard form. | Formula. Do not overwrite. | Actual date served. | Formula. Negative means the window was missed. | On time / LATE / Not served. | Your outgoing reference, so it is findable later. | Form, edition and clause. | T / T+M — which this event gives on this form. | Programme activity IDs where you have them. | Yes / No / Unknown. Record what you believed then. | Best estimate at the date of the notice. | As assessed. | The second-stage deadline, where the form sets one. | Actual date. | Baseline fragment / impacted fragment / daily reports / photos / correspondence. | Yes / No — and the ref of the competing cause. | Open / Substantiated / Assessed / Agreed / Rejected. | Anything a reader in two years would need.
EV-001 | Employer instruction 47 — revised riser layout, level 3 to 8 | 2026-09-04 | 2026-09-04 | 28 | 2026-10-02 | 2026-09-15 | 1900-01-16 | LATE | CN-012 | FIDIC 2017 SC 20.2.1 | T+M | M3-RISER-L3..L8 | Yes | 28 |  |  |  | Instruction · baseline fragment 04-09 · daily reports 04-09 to 02-10 | No | Open | Design issued 02-10; particulars in preparation
Formulas:
Notice due = IF(OR([Date first apparent]="",[Notice window (days)]=""),"",[Date first apparent]+[Notice window (days)])
Days to spare = IF(OR([Notice due]="",[Notice served]=""),"",[Notice due]-[Notice served])

## Legend
How to use this register
Yellow cells | Yours to fill in. One row per delay event.
Grey cells | Formulas — Notice due, Days to spare and Status calculate themselves. Do not overwrite them.
Row 7 | A worked example, in italic grey. Delete it or type over it.
Notice window | Read the number off the executed contract. Form defaults for orientation only: FIDIC 2017 SC 20.2.1 is 28 days from awareness; NEC4 clause 61.3 is 8 weeks; AIA A201–2017 §15.1.3.1 is 21 days; FAR 52.249-10(b)(1) is 10 days, extendable by the Contracting Officer; CCDC 2 – 2020 GC 6.5.4 is 10 Working Days and runs from commencement of the delay, not awareness. JCT DB 2024 clause 2.24.1 sets no fixed period.
Date first apparent | On most forms this is where the clock starts, so it is the most attacked date in the register. Record how you know it, in Notes.
Particulars due | The second-stage deadline where the form sets one — 84 days under FIDIC 2017 SC 20.2.4; three weeks for an NEC4 quotation under clause 62.3.
Working days | The Notice due formula adds calendar days. Where the contract counts working days, substitute =WORKDAY(D7,E7) and set the holiday list.
Why this exists | Three of the four elements of an extension of time claim are decided by what the project does while the works are going on. A register maintained weekly preserves a discrete, event-by-event causal case; the alternative is reconstructing commencement dates from memory months later.
Not legal advice | Illustrative template. Clause references are form-defaults and must be replaced with those in the executed contract.