TEMPLATE — CHECK AGAINST THE EXECUTED CONTRACT BEFORE USE

Extension of time — particulars checklist

What a substantiated extension of time submission carries, organised by the four elements it has to establish. Tick nothing you cannot point to a document for.

ELEMENT 1 — THE QUALIFYING EVENT

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The clause relied on, quoted from the executed contract with its form and edition | A submission that does not name its own clause is arguing in the abstract |
| ☐ | The instructing document, or the record of the condition | The primary fact. Everything downstream depends on its date |
| ☐ | Confirmation the event falls in the enumerated list, not a general appeal to fairness | FIDIC 2017 Sub-Clause 8.5 has no general sweep-up; several forms do |
| ☐ | Whether the event gives time only or time and money, on this form | The two lists diverge in every form, and differently in each |

ELEMENT 2 — CAUSATION TO COMPLETION

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The accepted baseline or last agreed programme as it stood at the event date, snapshotted | So the "before" state cannot be argued later |
| ☐ | The impacted fragment, isolated to this one event | A cumulative analysis will not satisfy a case-by-case requirement |
| ☐ | The critical-path comparison, before and after | Delay to progress is not delay to completion, and the analysis must show which happened |
| ☐ | The analysis method named, and why the records support it | Methodology must be driven by the factual evidence, not chosen for the answer it gives |
| ☐ | Every schedule logic change between updates, explained | Unexplained logic changes draw adverse inferences |
| ☐ | Daily reports across the impact window, with manpower and plant on the affected activity | A manpower drop is usually the first hard signal of when the impact began |
| ☐ | Dated photographs matched to the affected location | So the visual record lines up with the schedule fragment |

ELEMENT 3 — NOTICE AND PROCEDURE

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The notice itself, with proof of what was sent, to whom and when | The cheapest element to get right and the most common way entitlement is lost |
| ☐ | The date of awareness, evidenced — not asserted | On most forms the window runs from awareness; under CCDC 2 – 2020 GC 6.5.4 it runs from commencement of the delay |
| ☐ | The correspondence chain in date order, with attachments and acknowledgements | Acknowledgements fix when the thread last moved |
| ☐ | Any second-stage particulars served on their own deadline | 84 days under FIDIC 2017 Sub-Clause 20.2.4; three weeks for an NEC4 quotation under clause 62.3 |
| ☐ | Subcontractor notices served on the same facts, cross-referenced | A claim that ignores its own supply chain on the same event is easy to pick apart |

ELEMENT 4 — EXTENT

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The days claimed, added to the previously fixed completion date | Assessment is net, not gross — Balfour Beatty v Chestermount (1993) 62 BLR 1 |
| ☐ | Float identified, and how it was treated | Whether float is available to you is a contract question before it is a schedule question |
| ☐ | Any concurrent contractor-risk delay identified and addressed head-on | The answer varies from a full extension to none depending on governing law and form |
| ☐ | Prolongation priced for the period the effect was felt, not the tail of the job | Compensation runs to the period of impact, not the overrun weeks at the end |
| ☐ | The prolongation claim kept separate from any variation markup on the same event | Or the same cost is claimed twice under two headings and neither survives |

This checklist is illustrative and jurisdiction-neutral. It is not legal advice, and the deadlines and clause references above are form-defaults that must be replaced with the ones in the executed contract.