TEMPLATE — CHECK AGAINST THE EXECUTED CONTRACT BEFORE USE

Variation claim — submission checklist

What a substantiated variation claim carries, organised by the five elements it has to establish. Tick nothing you cannot point to a document for.

ELEMENT 1 — THE WORK IS OUTSIDE THE CONTRACT SCOPE

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The contract clause or drawing said to exclude the work, quoted | Scope is a question of contract construction, not of fairness or of how the parties behaved on site |
| ☐ | For a design and build job, the specific Employer's Requirements clause relied on | Anchor to a level of definition, not to RIBA-stage rhetoric. A stage statement is not a warranty |
| ☐ | Confirmation this is not underestimation of a lump sum scope | Getting the quantity wrong is the contractor's risk. Remeasurement gives the opposite answer on the same facts |
| ☐ | Where a provisional sum is involved, whether it was defined or undefined | Expenditure of a provisional sum is valued, not varied, and the programme consequence follows from the definition status |

ELEMENT 2 — THE CHANGE WAS INSTRUCTED

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The written instruction, or the confirmation letter that converted an oral direction | The commonest failure of all, and the most avoidable |
| ☐ | Evidence that the person who gave it holds the contractual authority to instruct changes | Authority is a separate question from writing, and on US public work it is a limit on capacity that estoppel cannot cure |
| ☐ | The date, checked against the contractual cut-off | The window closes. Under FIDIC Red Book 2017 (reprinted 2022) Sub-Clause 13.1, before the Taking-Over Certificate issues |
| ☐ | Where there is no instruction, the alternative route identified and pleaded in order | Instructed variation, then deemed or constructive, then waiver or estoppel, then restitution. Pleading restitution first concedes the ground you want |

ELEMENT 3 — PROCEDURAL COMPLIANCE

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The notice that the direction is regarded as a change | Three notices are required and claimants habitually give one |
| ☐ | The notice of price effect, on its own clause and its own deadline |  |
| ☐ | The extension of time notice, on a third clause and a third deadline | Missing the time notice does not defeat the valuation, and missing the valuation notice does not defeat the time |
| ☐ | The quotation, where a quotation procedure applies — priced for time and loss and expense, not only the direct work | Acceptance of a quotation is a final and inclusive settlement. A contractor that quotes only the direct work has settled the rest |
| ☐ | Proof of what was sent, to whom and when, for each of them |  |

ELEMENT 4 — VALUATION

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | The rung of the pricing ladder relied on, and why the rungs above it do not apply | You may not skip a rung because the answer further up suits you better |
| ☐ | Where a new rate is claimed, the contractual trigger satisfied and shown | FIDIC 2017 clause 12.3 sets numeric thresholds; JCT sets a judgment standard. They are different arguments |
| ☐ | The build-up, from first principles where a fair valuation is claimed | A fair valuation includes profit. It does not include head office overhead or prolongation |
| ☐ | Daywork records signed contemporaneously, if the daywork rung is reached | Daywork claims fail on records rather than on principle |
| ☐ | Preliminaries treated once, and once only | The valuation prices the changed work. Thickened and prolonged preliminaries travel by a different route under every form except NEC4 |

ELEMENT 5 — THE CLAIM SURVIVES WHAT CAME AFTER

|  | What the submission carries | Why it is asked for |
| --- | --- | --- |
| ☐ | Every executed change order reviewed for release language | Impact claims die in signed change orders, not in tribunals |
| ☐ | A reservation in the instrument itself, naming the claim, the event and the head of loss | A footer or a covering email is weaker than a reservation inside the document that carries the release |
| ☐ | The reservation repeated on every subsequent change order | A later unreserved signature can destroy an earlier reservation |
| ☐ | The impact on unchanged work identified and reserved by name | This is the head that gets released by accident |
| ☐ | The cumulative impact claim kept structured, not allowed to become a global claim | Cumulative impact is a recognised head with a recognised structure; a global claim is a pleading of last resort |

This checklist is illustrative and jurisdiction-neutral. It is not legal advice, and the deadlines and clause references above are form-defaults that must be replaced with the ones in the executed contract.